## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 952.5
|  | Actual: | 940.8333
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 3 | Operator | Initialise repository |  | 2026-02-09 08:30 | 2026-02-09 10:30 | Completed | 2 | 2 | 60 | 60 | Crear Proyecto, Repositorio, Invitar personas
2 | T0002/D | Development | Student 4 | Developer | Customise the starter | T0001/M | 2026-02-09 10:30 | 2026-02-09 11:30 | Completed | 1 | 1 | 25 | 25
3 | T0003/D | Development | Student 3 | Developer | Customise the starter | T0002/D | 2026-02-12 15:30 | 2026-02-12 17:30 | Completed | 1 | 2 | 25 | 50 | Añadir Banner, y textos personalizados
4 | T0004/D | Development | Student 3 | Developer | Implement feature | T0002/D | 2026-02-14 15:17 | 2026-02-14 19:47 | Completed | 4 | 4.5 | 100 | 112.5 | Crear Entidad Estrategia y Táctica
5 | T0005/M | Management | Student 3 | Manager | Write report |  | 2026-02-19 11:30 | 2026-02-19 13:30 | Completed | 2 | 2 | 100 | 100 | Hacer Documentación grupal
6 | T0006/M | Management | Student 3 | Manager | Make plans | T0004/D | 2026-02-21 16:45 | 2026-02-21 19:30 | Completed | 3 | 2.75 | 150 | 137.5 | Organizar Resto de tareas para esta entrega
7 | T0007/D | Development | Student 3 | Developer | Implement feature | T0006/M | 2026-02-25 15:21 | 2026-02-25 17:41 | Completed | 2 | 2.3333 | 50 | 58.3333 | Implementar Become Fundraiser
8 | T0008/D | Development | Student 3 | Developer | Implement feature | T0007/D | 2026-03-01 15:30 | 2026-03-01 18:30 | Completed | 3 | 3 | 75 | 75 | Implementar CRUD y Publish de Estrategias
9 | T0009/QA/T0008/D | QA | Student 3 | Tester | Test feature formally | T0008/D | 2026-03-01 18:30 | 2026-03-01 20:00 | Completed | 2 | 1.5 | 60 | 45 | Comprobar funcionalidades implementadas
10 | T0010/D | Development | Student 3 | Developer | Implement feature | T0008/D | 2026-03-19 10:00 | 2026-03-19 11:30 | Completed | 1.5 | 1.5 | 37.5 | 37.5 | Arreglar errores de intrusión
11 | T0011/QA/T0010/D | QA | Student 3 | Tester | Test feature formally | T0010/D | 2026-03-19 11:30 | 2026-03-19 14:00 | Completed | 3 | 2.5 | 90 | 75 | Comprobación funcionamiento intrusion alert
12 | T0012/QA/T0010/D | QA | Student 3 | Tester | Test performance formally | T0010/D | 2026-03-20 16:30 | 2026-03-20 19:30 | Completed | 4 | 3 | 120 | 90 | Comprobacion general del script de evaluación
13 | T0013/M | Management | Student 3 | Operator | Package deliverable |  | 2026-03-20 19:30 | 2026-03-20 20:00 | Completed | 0.5 | 0.5 | 15 | 15 | Empaquetar Proyecto
14 | T0014/M | Management | Student 3 | Operator | Upload deliverable | T0013/M | 2026-03-20 20:00 | 2026-03-20 20:30 | Completed | 0.5 | 0.5 | 15 | 15 | Subir Proyecto
15 | T0015/M | Management | Student 3 | Tester | Test performance formally | T0013/M | 2026-03-20 20:30 | 2026-03-20 21:50 | Completed | 1 | 1.5 | 30 | 45 | Comprobar Funcionamiento del Proyecto del Zip entregado
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 525
|  | Actual: | 525
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/R/ | Revision | Student 3 | Analyst | Elicit requirements |  | 2026-03-12 09:00 | 2026-03-12 11:00 | Completed | 2 | 2 | 80 | 80 | Escribir requisitos descomponiendolos en Funcionales, No funcionales …
2 | T0002/R/ | Revision | Student 3 | Student | Attend lecture |  | 2026-03-13 08:30 | 2026-03-13 10:30 | Completed | 2 | 2 | 0 | 0 | Asistir al Follow Up (Vimos detalladamente los requisitos)
3 | T0003/M | Management | Student 3 | Manager | Make plans | T0001/R/ | 2026-03-13 10:30 | 2026-03-13 11:30 | Completed | 1.5 | 1.5 | 75 | 75 | Planificar Tareas para esta entrega
4 | T0004/M | Management | Student 3 | Analyst | Create domain model | T0001/R/ | 2026-03-15 10:00 | 2026-03-15 12:00 | Completed | 2 | 2 | 80 | 80 | Modelar Entidades Nivel B
5 | T0005/M | Management | Student 3 | Analyst | Define features | T0001/R/ | 2026-03-15 12:00 | 2026-03-15 13:00 | Completed | 1 | 1 | 40 | 40 | Defnir Features exactas para esta entrega
6 | T0006/D | Development | Student 3 | Developer | Implement feature | T0005/M | 2026-03-15 10:00 | 2026-03-15 20:00 | Completed | 10 | 10 | 250 | 250 | Implementar requisitos B/1 y B/2
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2026-02-09 08:30
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O